## Sheet1
ID | Risk Description | Asset / Process | Risk Category | Likelihood (1–5) | Impact (1–5) | Risk Score | Controls in Place | Residual Risk | Risk Owner | Review Frequency | Status | Policy Control Mapping
RSK-001 | Publicly accessible S3 bucket with PII data | AWS S3 Storage | Cloud Security | 4 | 5 | 20 | S3 access policies, AWS Config alerts | Medium | Cloud Security Lead | Monthly | Open | cloud-security-policy.md
RSK-002 | Aadhaar data stored without encryption at rest | MySQL Database | Data Privacy | 5 | 5 | 25 | DB-level encryption planned | High | Database Admin | Monthly | Open | data-protection-policy.md
RSK-003 | Hardcoded API keys for Razorpay in source code | Payment API Integration | Third-Party Risk | 4 | 4 | 16 | Code reviews, key rotation policy | Medium | DevSecOps Engineer | Quarterly | Monitoring | data-protection-policy.md
RSK-004 | Developers have production DB write access | MySQL Database | Insider Threat | 3 | 5 | 15 | Role-based access under review | Medium | IT Manager | Monthly | Open | cloud-security-policy.md
RSK-005 | Lack of centralized log monitoring | Logging System | Monitoring & Logging | 4 | 3 | 12 | Wazuh implementation in progress | Medium | Security Analyst | Quarterly | Monitoring | cloud-security-policy.md
RSK-006 | No formal vendor assessment for Digilocker API | Third-Party Integration | Third-Party Risk | 3 | 4 | 12 | Basic SLA review | Medium | Compliance Officer | Yearly | Open | data-protection-policy.md
RSK-007 | No documented incident response plan | IT Security Governance | Incident Response | 4 | 4 | 16 | IR plan drafting initiated | High | CISO | Quarterly | Open | incident-response-policy.md